## Slide 1: SOFTWARE DEVELOPMENT PROJECT MANAGEMENT (CSC4125)
Lecture 3: Process & Phases

## Slide 2: Project Management
Project management is the application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.
  Application of knowledge requires the effective management of the project processes

## Slide 3: When does the end of the project reached?
The end of the project is reached when one or more of the following is true:
  The project’s objectives have been achieved
  The objectives will not or cannot be met
  Funding is exhausted or no longer available for allocation to the project
  The need for the project no longer exists
  The human or physical resources are no longer available
  The project is terminated for legal or convenience

## Slide 4: Process
A process is a set of interrelated actions and activities performed to create a pre-specified product, service, or result.
  Each process is characterized by it inputs, the tools and techniques that can be applied, and the resulting outputs

## Slide 5: Process
All of the work that’s done on a project is made up of processes.
There’s a pattern to all of the work that gets done on the project
  Plan
  Work
    Compare with original plan
    If off-plan, corrections are made and everything needs to get back on track
Process framework, Process groups and Knowledge areas ensures project smoothness.

## Slide 6: Process Groups
Process Groups (or Project Management Process Groups):
  A logical grouping of project management inputs, tools and techniques, and outputs
  Process Groups are the steps of a project
Process groups are required for any project
Process groups cover what we need to DO
Have clear dependencies and are typically performed in each project and highly interact with one another.
Note: Process groups are not project phases. In fact, it is possible that all Process Groups could be conducted within a Project Phase.

## Slide 7: Process Groups
Project management processes are grouped in five Project Management Process Groups:
  Initiating Process Group
  Planning Process Group
  Executing Process Group
  Monitoring & Controlling Process Group
  Closing Process Group

## Slide 8: [1] Initiating Process Group
  The processes performed to define a new project or a new phase of an existing project by obtaining authorization to start the project/phase.
  If not already assigned, the project manager will be selected
  Align the stakeholders’ expectations with the project’s purpose, give them visibility about scope and objectives
  Identify stakeholders and develop Project Charter
  Project charter is a document issued by the project initiator/sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities
  Develop preliminary project scope statement
  Requirement and System Analysis

## Slide 9: [2] Planning Process Group
  The processes required to establish the scope of the project, refine the objectives, and define the course of action required to attain the objectives.
  Develop Project Management Plan (Why the project? What to deliver? Who do what? When accepted? How executed?) and the project documents that will be used to carry out the project.
  Project management plan is the document that describes how the project will be executed, monitored, and controlled
  Establish total scope of the effort, define & refine the objectives, develop the course of action required to attain those objectives.
  Estimation & Resource allocation.
  Project management plan and project documents developed as outputs from the Planning Process Group will explore all aspects of the scope, time, cost, quality, communications, human resources, risks, procurements, and stakeholder engagement.

## Slide 10: [3] Executing Process Group
  Implementation
  The processes performed to complete the work defined in the project management plan to satisfy the project requirements.
  Involves coordinating people and resources, manage stakeholder expectations, as well as integrating & performing the activities of the project in accordance with the project management plan.
  A large portion of project’s budget will be expended in performing Executing Process Group processes.
  May need to modify project management plan

## Slide 11: [4] Monitoring & Controlling Process Group
The processes required to track, review, and regulate the progress & performance of the project; identify any areas in which changes to the plan are required; and initiate the corresponding changes.
  Track progress
  Adjust as required
Monitor & control project work and integrate change control
  Make sure only approved changes are incorporated
Usually performed at regular intervals

## Slide 12: [5] Closing Process Group
  The processes performed to formally complete or close a project, phase, or contract.
  Finalize all activities across all process groups to formally close the project/phase.
  Either project finished or cancelled
    Objective : Successful completion of the project
At project/phase closure, the following may occur
  Obtain acceptance by the customer/sponsor to formally close the project/phase
  Conduct post-project or phase-end review
  Document lessons learned
  Close out all procurement activities
  Perform team members’ assessments & release project resources

## Slide 13: Project Phases
Project Phase: A collection of logically related project activities that culminates in the completion of one or more deliverables.
If the project is really big, then it can be managed in Phases.
  A project may be divided into any number of phases
Project phases typically are completed sequentially, but can overlap in some project situations.

## Slide 14: Project Phases
Different phases typically have a different duration/effort.
Each phase of the project goes through all five process groups.
The number of phases, the need for phases and the degree of control applied depend on the size, complexity and potential impact of the project.

## Slide 15: Phase-to-Phase Relationships
Sequential Relationship
  When a project has sequential phases, each phase starts after the previous phase is 100% complete
Overlapping Relationship
  In an overlapping relationship, a phase starts prior to the completion of the previous phase.
Iterative Relationship
  A project got a single team performing the Initiating and Planning Processes for one phase, while also doing the Executing processes for the previous phase. That way, when the Executing and Closing process groups are finished, the team can jump straight into the next phase’s Executing processes.

## Slide 16: Processes
Within each process group are individual processes, which is how actually the work is actually done in a project.
According to PMBOK Guide (6th Edition), every project breaks down into 49 processes.
Each of the processes belongs to only one process groups.

## Slide 17: Processes (cont.)
Process Magnets: (Some of the 49 processes)
Initiating Process Group (2 processes)
  Develop Project Charter
  Identify Stakeholders
Planning Process Group (24 processes)
  Develop Project Management Plan
  Plan Scope Management
  Collect Requirements
  Define Scope
  Create WBS
  Plan Schedule Management
  Plan Risk Management
  Plan Quality Management
  Estimate Activity Durations
  …

## Slide 18: Processes (cont.)
Executing Process Group (10 processes)
  Direct & Manage Project Execution
  Manage Project Knowledge
  Manage Quality
  Acquire Resources
  Develop Team
  Manage Team
  Manage Communications
  Manage Stakeholder Engagement
  …

## Slide 19: Break It Down (cont.)
Monitoring and Controlling Process Group (12 processes)
  Monitor and Control Project Work
  Perform Integrated Change Control
  Validate Scope
  Control Scope
  Control Schedule
  Control Costs
  Control Quality
  Monitor Stakeholder Engagement
  …
Closing Process Groups (1 process)
  Close Project or Phase

## Slide 20: Anatomy of Processes
A process is a systematic series of activities directed towards causing an end result such that one or more inputs will be acted upon to create one or more outputs.
INPUTS
  Information that are used in projects
TOOLS & TECHNIQUES
  All project work
  Takes inputs and turns them into outputs
OUTPUTS
  Documents, Deliverables and Decisions
  Helps project come in on time, within budget and with high quality

## Slide 21: Anatomy of Processes (cont.)
Sometimes the output of one process becomes an input of the next process.
The process groups help in organizing the processes by the kind of work that is done.
The knowledge areas help in organizing by the subject matter that’s being dealt with.

## Slide 22: Project Management Knowledge Areas
The Project Management Knowledge Areas are fields or areas of specialization that are commonly employed when managing projects.
A Knowledge Area is a set of processes associated with a particular topic in project management.
There are 10 Knowledge Areas that are used on most projects most of the time.

## Slide 23: Project Management Knowledge Areas
According to PMBOK GUIDE (6th edition), there are 10 Knowledge Areas:
  Project Integration Management
  Project Scope Management
  Project Schedule Management
  Project Cost Management
  Project Quality Management
  Project Resource Management
  Project Communications Management
  Project Risk Management
  Project Procurement Management
  Project Stakeholder Management

## Slide 24: Project Management Knowledge Areas
  Project Integration Management
  Includes the processes and activities to identify, define, combine, unify, and coordinate the various processes and project management activities within the Project Managements Process Groups
  Making sure all the right parts of the project come together in the right order, at the right time
  Coordinating all of the work so that it happens correctly

## Slide 25: Project Management Knowledge Areas
2) Project Scope Management
  Includes the processes required to ensure that the project includes all the work required, and only the work required, to complete the project successfully
  The processes are organized in two ways – the process groups are about how you do the work, and the knowledge areas are there to help you categorize them and help you learn
  Figuring out what work needs to be done for your project. Making sure your end product has everything you said it would

## Slide 26: Project Management Knowledge Areas
Project Schedule Management
  Includes the processes required to manage the timely completion of the project.
  Preparation and Implementation time.
  Figuring out the time it will take to do your work and the order you need to do it in. Tracking your schedule and making sure everything gets done on time.

## Slide 27: Project Management Knowledge Areas
Project Cost Management
  Includes the processes involved in planning, estimating, budgeting, financing, funding, managing, and controlling costs so the project can be completed within the approved budget
  Knowing how much you’re able to invest in the project and making sure you spend it right

## Slide 28: Project Management Knowledge Areas
Project Quality Management
  Includes the processes for incorporating the organization’s quality policy regarding planning, managing, and controlling project and product quality requirements, in order to meet stakeholders’ expectations.
  Making sure that output maintains standard.
  Making sure you work as efficiently as you can and don’t add defects into the product.

## Slide 29: Project Management Knowledge Areas
6) Project Resource Management
  Includes the processes to identify, acquire, and manage the resources needed for the successful completion of the project
  Efficient use of schedules
  Getting the people to work on the team and helping them stay motivated. Rewarding them for a job well done and resolving conflicts that come up.

## Slide 30: Project Management Knowledge Areas
Project Communications Management
  Includes the processes required to ensure timely and appropriate planning, collection, creation, distribution, storage, retrieval, management, control, monitoring, and ultimate disposition of project information
  Making sure that consistent communications are maintained
  Making sure that everybody knows what they need to know to do the job right. Tracking how people talk to each other and dealing with gaps if they happen.

## Slide 31: Project Management Knowledge Areas
Project Risk Management
  Includes the processes of conducting risk management planning, identification, analysis, response planning, response implementation, and monitoring risk on a project
  Figuring out how to protect your project from anything that could happen to it
  Risk Management can also be about making sure that you are in the right position to take advantage of the opportunities that come your way

## Slide 32: Project Management Knowledge Areas
Project Procurement Management
  Includes the processes necessary to purchase or acquire products, services, or results needed from outside the project team
  Selecting the right source for resources
  Finding contractors to help you do the work. Setting the ground rules for their relationships with your company.

## Slide 33: Project Management Knowledge Areas
10) Project Stakeholder Management
  Includes the processes required to identify the people, groups, or organizations that could impact or be impacted by the project, to analyze stakeholder expectations and their impact on the project, and to develop appropriate management strategies for effectively engaging stakeholders in project decisions and execution.

## Slide 34: Process Groups vs. Knowledge Areas
Question: Are Process Groups and Knowledge Areas same thing?
Answer: No, not really..
Process groups and Knowledge Areas are two different ways to organize the processes … but they don’t really overlap each other!
Process groups divide up the processes by function.
Knowledge areas divide the same processes up by subject matter.
Every process belong to exactly one process group.
Every process is in exactly one knowledge area

## Slide 35: Process Groups vs. Knowledge Areas
Project Management Process Groups are NOT the same as Project Phases.
  For example, in a software project, the Project Phases could be Requirements Analysis, Design, Coding, Testing, Release etc. As you can see, these are clearly different from the five Process Groups. When a large project is divided into phases, all five Process Groups would be repeated in each phase.
When Project Management processes are grouped by areas of specialization, they form Knowledge Areas.
When Project Management processes are grouped logically, they form Process Groups.
The Knowledge Areas describe what a project manager needs to know, and the Process Groups describe what a project manager needs to do.